## Agile Documentation
Milestone / Sprint | Duration | Sprint Goal | Planned Activities | Completed Work | Status | Deliverables / Evidence
Milestone 1 | Week 1-2 | Set up platform foundation. | Workflow, architecture, SQLite, Flask, authentication, session lifecycle, photo capture, synthetic data. | Foundation, authentication, sessions, photo capture and database implemented. | Completed | app.py, database.py, authentication/session workflow.
Milestone 2 | Week 3-4 | Implement monitoring and suspicious-event detection. | Face monitoring, face-absence logging, browser events and threshold rules. | Face monitoring, browser logging, thresholds, alerts and evidence implemented/tested. | Completed | Face events, browser events, HIGH alerts, evidence.
Milestone 3 | Week 5-6 | Build scoring, analytics, AI reporting and evidence. | Integrity scoring, analytics, K-Means, cohort profiling, AI report agent, alerts/evidence. | Scoring, analytics, clustering, risk profiling, reports, alerts/evidence completed. | Completed | ai_report_agent.py, scoring, analytics outputs, alerts/evidence.
Milestone 5 | Week 7-8 | Integrate dashboard, exports and final validation. | Streamlit dashboard, JSON/CSV export, end-to-end testing, bug fixes and documentation. | Dashboard, export, final testing, README, LICENSE and documentation prepared. | Completed | app/dashboard.py, exports, README.md, LICENSE.